## Slide 1
2026
MOP LAUNCHING
DRAFT PLAN
Prepared by Khoi Ta

## Slide 2
MOP Launching - Order Wall

## Slide 3
Fanpage, IG, Tiktok, Threads
In-app push, in-store POSM
Fanpage, IG, Tiktok, Threads
In-app push, in-store POSM
Community Group
Introduce MOP as an convenience and friendly ways to enjoy good moments with McD
[owned] Exclusive bonus points / in-app offers
Partners’ offers
[owned] Crew competition
Lucky draw: 3 rewards
[owned] Store activation
Intro clip + key visual
[owned] Exclusive bonus points / in-app offers
Partners’ offers
[owned] Crew competition
Lucky draw announcement
3
1
2
Fanpage, IG, Tiktok, Threads
In-app push, in-store POSM
Community Group
Reinforce “Feel Good Moment” by offering customers new GMAL feature. Whether you are eating in the restaurant or enjoy food at home, it’s always the most convenient experience
Animation for all app features
Exclusive offer & merch from McD & partners
[owned] Crew competition
Lucky draw: 2 rewards
MOP Campaign Roadmap (reference)
AWARENESS: 25/5 - 14/6 (3 wks)
AMPLIFIED: 15/6 - 12/7 (4 wks)
Trigger FOMO to drive customers to the store to try for themselves
RETAIN: 13/7 - 7/8 (4 wks)
An all-rounder app in your hand: not just MOP but also earn & burn points for exclusive moments

## Slide 8
Master timeline
MOP Launching - Expected Timeline
Market kick off & market prework - configuration
mid Jan - mid Feb
Market acceptance testing
mid Feb - 6 weeks
Pilot
Apr
Com Plan Development
mid March - mid Apr
Market activation
mid May - 2 weeks
MOP campaign launching
Last week of May / 1st week of June

## Slide 11
Hạng mục (Category) | Tỷ trọng (%) | TỔNG CAMPAIGN |  | AWARENESS |  | AMPLIFIED |  | RETAIN | 
 |  | Ngân sách (VNĐ) | KPI (Installs) | Ngân sách (VNĐ) | KPI (Installs) | Ngân sách (VNĐ) | KPI (Installs) | Ngân sách (VNĐ) | KPI (Installs)
Crew Incentive (Thưởng đội ngũ) | 9% | 100,000,000 | 15,000 | 40.000.000 | 6.000 | 30.000.000 | 4.500 | 30.000.000 | 4.500
Partnership Offers (Ưu đãi đối tác) | 26% | 300,000,000 | 6,000 | 120.000.000 | 2.400 | 90.000.000 | 1.800 | 90.000.000 | 1.800
Exclusive Offers (Ưu đãi độc quyền) | 13% | 150,000,000 | 3,000 | 60.000.000 | 1.200 | 45.000.000 | 900 | 45.000.000 | 900
Giải thưởng (Bốc thăm may mắn) | 14% | 160,000,000 | 3,200 | 56.000.000 | 1.120 | 42.000.000 | 840 | 42.000.000 | 840
Vận hành + Registration (POSM) | 12% | 140,000,000 |  | 0 |  | 0 |  | 0 | 
Social seeding (Paid media) | 26% | 300,000,000 |  |  |  |  |  |  | 
TỔNG CỘNG | 100% | 1,150,000,000 | 27,200 | 276,000,000 | 12.800 | 207.000.000 | 9.600 | 207.000.000 | 9.600
Detailed Budget Breakdown (Updated)

## Slide 12
Thank you