## Detailed
MASTER TIMELINE | [49 empty] | done
in progress
actual done
TO DO LIST | PIC | Note | Status | AUG | [16 empty] | JAN | [26 empty] | FEB | [27 empty] | MAR | [30 empty] | APR | [29 empty] | MAY | [30 empty] | JUN | [29 empty] | JULY | [30 empty] | AUG
|  |  |  | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 1 | 2 | 3 | 4 | 5 | 6 | 7 | 8 | 9 | 10 | 11 | 12 | 13 | 14 | 15 | 16 | 17 | 18 | 19 | 20 | 21 | 22 | 23 | 24 | 25 | 26 | 27 | 28 | 29 | 30 | 31 | 1 | 2 | 3 | 4 | 5 | 6 | 7
PLANNING & DISCOVERY
Questionaire | bar: JAN 9
Localization builds | bar: JAN 9
Charter prep & Sign off | bar: JAN 9
MARKET PREPARATION
1. Market Kick-off
1.1 Market engagement & planning |  | 30 Jul | bar: JAN 30
1.2 MOP Overview & Pre requisites explained | bar: JAN 30
1.3 Market cross functional stakeholders engagement | bar: JAN 30
2. Market prework & configuration
2.1 RFM: Products, images and screens |  | 3 wks (20 Jul)
2.2 Translations: PhraseApp and Backend
2.3 Network set up
2.4 Legal : Contracts signed (Adyen, SIFT) |  | 3-4 wks (20 Jul)
2.5 Legal: Consent , T&Cs
2.6 Training/walkthrough (Configuration, UI UX, Payment, Ops, Reporting) |  | 19 Jul - 12 Aug 7 sessions | bar: FEB 2; FEB 4; FEB 6; FEB 9; FEB 11; FEB 13
2.7 Image Generation
2.8 AWS connectivity
2.9 SIFT and Adyen Onboarding
2.10 Backend Configuration
2.11 Plexure and GMAL configuration
DEPLOY / ACTIVATE
3. Market acceptance testing
3.1 Local Lab build and testing |  | 3 wks (16 Aug) Will be testing for 2 rounds
3.2 Backend and Adyen lab set up
3.3 Front end MOP set up
3.4 Issues / defect identification and management
3.5 RFM package build for pilot
3.6 Pilot training for Crew
3.7 Back end stores onboarding |  | 2 - 4 wks (23 Aug) | bar: MAR 4 to MAR 6; MAR 30 to APR 1
3.8 Adyen store onboarding | bar: MAR 4 to MAR 6; MAR 30 to APR 1
4. Pilot
4.1 Pilot preparation |  | 6 wks (30 Aug)
4.2 Single store pilot
4.3 Extended pilot
5. NDR/Activation
5.1 National Activation Preparation |  | 4 wks (18 Oct)
5.2 National Activation
AWARENESS & TRIAL CAMPAIGN
6.1 Agency briefing & NDA signed off |  | 12 wks | bar: MAR 23 to MAR 26
6.2 Agency present & Revisions (2 rounds) | bar: MAR 27; APR 13 to APR 16
6.3 Announcement
6.4 Contract signed off & deposit
6.5 Assets preping | bar: MAY 18 to MAY 20
6.6 Campaign kick-off & execution
6.7 Wrap up & Report